## Dashboard
EMPLOYEE TASK MANAGEMENT DASHBOARD
Last Updated: 11-Aug-2026 01:27
Total Employees |  | Total Tasks |  | Completed Tasks |  | In Progress | Pending Tasks | Delayed Tasks | Status | Count |  | Priority | Count
10 |  | 15 |  | 2 |  | 9 | 4 | 2 | To Do | 3 |  | Critical | 2
[9 empty] | In Progress | 9 |  | High | 5
Overall Completion Rate | [8 empty] | On Hold | 1 |  | Medium | 5
13.33% | [8 empty] | Completed | 2 |  | Low | 3
[9 empty] | Cancelled | 0
[9 empty] | Employee | Total | Completed |  | Week | Tasks Due
[9 empty] | John | 2 | 0 |  | Week 30 | 0
[9 empty] | Emily | 2 | 0 |  | Week 31 | 0
[9 empty] | Michael | 2 | 1 |  | Week 32 | 2
[9 empty] | Sarah | 2 | 1 |  | Week 33 | 6
[9 empty] | David | 1 | 0 |  | Week 34 | 4
[9 empty] | Jessica | 2 | 0 |  | Week 35 | 3
[9 empty] | Robert | 1 | 0
[9 empty] | Lisa | 1 | 0
[9 empty] | James | 1 | 0
[9 empty] | Amanda | 1 | 0
⚠️ OVERDUE TASKS
Task ID | Employee | Task Title | Priority | Due Date | Days Overdue
TSK002 | Emily Davis | Bug Fixes | Critical | 2026-08-10 | 1
TSK007 | Robert Taylor | Financial Report | High | 2026-08-10 | 1

## Employee Master
Employee ID | Employee Name | Department | Designation | Manager | Email | Joining Date | Employment Status
EMP001 | John Smith | Engineering | Senior Developer | Sarah Johnson | john.smith@company.com | 2022-03-15 | Active
EMP002 | Emily Davis | Engineering | Developer | John Smith | emily.davis@company.com | 2023-01-10 | Active
EMP003 | Michael Brown | Marketing | Marketing Manager | David Wilson | michael.brown@company.com | 2021-06-20 | Active
EMP004 | Sarah Johnson | Engineering | Engineering Lead | David Wilson | sarah.johnson@company.com | 2020-09-01 | Active
EMP005 | David Wilson | Management | Director |  | david.wilson@company.com | 2019-01-15 | Active
EMP006 | Jessica Lee | HR | HR Manager | David Wilson | jessica.lee@company.com | 2021-02-28 | Active
EMP007 | Robert Taylor | Finance | Financial Analyst | Lisa Anderson | robert.taylor@company.com | 2022-07-05 | Active
EMP008 | Lisa Anderson | Finance | Finance Manager | David Wilson | lisa.anderson@company.com | 2020-11-10 | Active
EMP009 | James Martinez | Marketing | Marketing Specialist | Michael Brown | james.martinez@company.com | 2023-04-01 | Active
EMP010 | Amanda White | Engineering | QA Engineer | Sarah Johnson | amanda.white@company.com | 2022-10-15 | Active

## Task Management
Task ID | Employee ID | Employee Name | Department | Task Title | Task Description | Priority | Assigned Date | Start Date | Due Date | Completed Date | Status | Progress % | Estimated Hours | Actual Hours | Assigned By | Dependency | Remarks | Days Remaining | Delay Status
TSK001 | EMP001 | John Smith | Engineering | API Development | Develop REST API endpoints for user module | High | 2026-08-01 | 2026-08-02 | 2026-08-15 |  | In Progress | 60% | 40 | 30 | Sarah Johnson |  | On track | 4 | On Track
TSK002 | EMP002 | Emily Davis | Engineering | Bug Fixes | Fix critical bugs in payment module | Critical | 2026-08-03 | 2026-08-03 | 2026-08-10 |  | In Progress | 80% | 16 | 14 | John Smith | TSK001 | High priority | 0 | Delayed
TSK003 | EMP003 | Michael Brown | Marketing | Campaign Planning | Q3 marketing campaign strategy | High | 2026-08-01 | 2026-08-01 | 2026-08-20 |  | In Progress | 45% | 30 | 15 | David Wilson |  |  | 9 | On Track
TSK004 | EMP004 | Sarah Johnson | Engineering | Architecture Review | Review system architecture for scalability | Medium | 2026-07-25 | 2026-07-26 | 2026-08-08 | 2026-08-07 | Completed | 100% | 20 | 18 | David Wilson |  | Completed early | 0 | Completed
TSK005 | EMP005 | David Wilson | Management | Budget Review | Q3 budget review and approval | High | 2026-08-05 | 2026-08-06 | 2026-08-12 |  | In Progress | 50% | 10 | 5 |  |  |  | 1 | Due Soon
TSK006 | EMP006 | Jessica Lee | HR | Recruitment Drive | Hire 5 new developers | Medium | 2026-07-15 | 2026-07-16 | 2026-08-30 |  | In Progress | 40% | 60 | 25 | David Wilson |  |  | 19 | On Track
TSK007 | EMP007 | Robert Taylor | Finance | Financial Report | Prepare monthly financial report | High | 2026-08-01 | 2026-08-02 | 2026-08-10 |  | To Do | 0% | 15 | 0 | Lisa Anderson |  | Not started | 0 | Delayed
TSK008 | EMP008 | Lisa Anderson | Finance | Audit Preparation | Prepare documents for annual audit | Critical | 2026-07-20 | 2026-07-21 | 2026-08-15 |  | In Progress | 70% | 50 | 40 | David Wilson |  |  | 4 | On Track
TSK009 | EMP009 | James Martinez | Marketing | Social Media | Execute social media campaign | Low | 2026-08-05 | 2026-08-06 | 2026-08-25 |  | To Do | 0% | 20 | 0 | Michael Brown | TSK003 | Waiting for campaign approval | 14 | On Track
TSK010 | EMP010 | Amanda White | Engineering | Test Automation | Create automated test suite | Medium | 2026-08-01 | 2026-08-02 | 2026-08-18 |  | In Progress | 55% | 35 | 20 | Sarah Johnson | TSK001 |  | 7 | On Track
TSK011 | EMP001 | John Smith | Engineering | Code Review | Review code for new features | Medium | 2026-08-08 | 2026-08-09 | 2026-08-14 |  | To Do | 0% | 8 | 0 | Sarah Johnson |  |  | 3 | Due Soon
TSK012 | EMP002 | Emily Davis | Engineering | Documentation | Update API documentation | Low | 2026-08-06 | 2026-08-07 | 2026-08-20 |  | On Hold | 20% | 12 | 3 | John Smith | TSK001 | Waiting for API completion | 9 | On Track
TSK013 | EMP003 | Michael Brown | Marketing | Competitor Analysis | Analyze competitor marketing strategies | High | 2026-07-28 | 2026-07-29 | 2026-08-05 | 2026-08-06 | Completed | 100% | 25 | 28 | David Wilson |  | Completed with delay | 0 | Completed
TSK014 | EMP004 | Sarah Johnson | Engineering | Team Training | Conduct training on new tools | Medium | 2026-08-10 | 2026-08-11 | 2026-08-17 |  | In Progress | 30% | 16 | 5 | David Wilson |  |  | 6 | On Track
TSK015 | EMP006 | Jessica Lee | HR | Policy Update | Update employee handbook | Low | 2026-08-01 | 2026-08-02 | 2026-08-30 |  | In Progress | 25% | 20 | 5 | David Wilson |  |  | 19 | On Track
Formulas:
Days Remaining = IF(OR(TaskTable[[#This Row],[Status]]="Completed",TaskTable[[#This Row],[Status]]="Cancelled"),0,IF(TaskTable[[#This Row],[Due Date]]="","",MAX(0,TaskTable[[#This Row],[Due Date]]-TODAY())))

## Weekly Task View
Weekly Task View
Current Week: | 33
Week | Employee Name | Task Title | Priority | Status | Progress % | Due Date | Est. Hours
33 | John Smith | API Development | High | In Progress | 60% | 2026-08-15 | 40
33 | Emily Davis | Bug Fixes | Critical | In Progress | 80% | 2026-08-10 | 16
34 | Michael Brown | Campaign Planning | High | In Progress | 45% | 2026-08-20 | 30
32 | Sarah Johnson | Architecture Review | Medium | Completed | 100% | 2026-08-08 | 20
33 | David Wilson | Budget Review | High | In Progress | 50% | 2026-08-12 | 10
36 | Jessica Lee | Recruitment Drive | Medium | In Progress | 40% | 2026-08-30 | 60
33 | Robert Taylor | Financial Report | High | To Do | 0% | 2026-08-10 | 15
33 | Lisa Anderson | Audit Preparation | Critical | In Progress | 70% | 2026-08-15 | 50
35 | James Martinez | Social Media | Low | To Do | 0% | 2026-08-25 | 20
34 | Amanda White | Test Automation | Medium | In Progress | 55% | 2026-08-18 | 35
33 | John Smith | Code Review | Medium | To Do | 0% | 2026-08-14 | 8
34 | Emily Davis | Documentation | Low | On Hold | 20% | 2026-08-20 | 12
32 | Michael Brown | Competitor Analysis | High | Completed | 100% | 2026-08-05 | 25
34 | Sarah Johnson | Team Training | Medium | In Progress | 30% | 2026-08-17 | 16
36 | Jessica Lee | Policy Update | Low | In Progress | 25% | 2026-08-30 | 20

## Monthly Summary
Monthly Employee Performance Summary
Report Month: | August 2026
Employee Name | Total Tasks | Completed Tasks | In Progress Tasks | Pending Tasks | Delayed Tasks | Completion Rate % | Total Est. Hours | Total Actual Hours
John Smith | 2 | 0 | 1 | 1 | 0 | 0% | 48 | 30
Emily Davis | 2 | 0 | 1 | 1 | 1 | 0% | 28 | 17
Michael Brown | 2 | 1 | 1 | 0 | 0 | 50% | 55 | 43
Sarah Johnson | 2 | 1 | 1 | 0 | 0 | 50% | 36 | 23
David Wilson | 1 | 0 | 1 | 0 | 0 | 0% | 10 | 5
Jessica Lee | 2 | 0 | 2 | 0 | 0 | 0% | 80 | 30
Robert Taylor | 1 | 0 | 0 | 1 | 1 | 0% | 15 | 0
Lisa Anderson | 1 | 0 | 1 | 0 | 0 | 0% | 50 | 40
James Martinez | 1 | 0 | 0 | 1 | 0 | 0% | 20 | 0
Amanda White | 1 | 0 | 1 | 0 | 0 | 0% | 35 | 20
TOTAL | 15 | 2 | 9 | 4 | 2 | 13.33% | 377 | 208